## Initiate
Project NAME / Manager
PROJECT Initiate | VALUE | SCORE | WEIGHT
1/ Is the Project the output of a "Formal" request system |  |  | 30
Yes = 1 | 0 | 0
No = 4 | 4 | 120
| SCORE | 120
NOTES:
2/ Is sponsorship formalized by a signature |  |  | 30
Yes = 1 | 0 | 0
No = 4 | 4 | 120
| SCORE | 120
NOTES:
3/ What is the Project Dollar Value |  |  | 40
Less Than $50,000 = 1 | 0 | 0
$50,000 to 100,000 = 2 | 2 | 80
$100,000 to $450,000 = 3 | 0 | 0
Over $450,000 = 4 | 0 | 0
| SCORE | 80
NOTES:
4/ What is the number of Estimated Resource Hours |  |  | 40
Less than 300 = 1 | 0 | 0
301 to 750 = 2 | 2 | 80
751 to 1500 = 3 | 0 | 0
Greater Than 1500 hours = 4 | 0 | 0
| SCORE | 80
NOTES:
5/ Does request have a formal approval / review process to proceed |  |  | 40
Yes = 1 | 0 | 0
Informal Review = 3 | 3 | 120
No = 4 | 0 | 0
| SCORE | 120
NOTES:
6/ How many interfaces are predicted |  |  | 30
Less than 10 = 1 | 1 | 30
10 to 50 = 2 | 0 | 0
50 to 100 = 3 | 0 | 0
Greater Than 100 = 4 | 0 | 0
| SCORE | 30
NOTES:
7/ Will project be managed by outside vendor |  |  | 40
Internally controlled = 1 | 0 | 0
Somewhat Vendor dependant = 2 | 0 | 0
Very dependant on vendor for management = 3 | 3 | 120
Totally dependant minimum internal monitoring = 4 | 0 | 0
| SCORE | 120
8/ Will project affect / impact a mission critical application system |  |  | 50
Yes = 3 | 3 | 150
Don't Know = 4 | 0
No = 1 | 0 | 0
| SCORE | 150
9/ Has project been reviewed and approved by a formal process? |  |  | 30
Yes = 1 | 0 | 0
Don't Know = 3 | 3 | 90
No = 4 | 0 | 0
| SCORE | 90
NOTES:
TOTAL RISK RATING
Low Risk 01 - 330
Medium Risk 331 - 540
High Risk 541 - xxx
| TOTAL SCORE | 820
Note on A39: Colonial:
Note on A56: Colonial:

## Manager
PROJECT MANAGER | Value | Score | Weight
1/ Project Manager an contractor / vendor |  |  | 50
Yes = 4 | 4 | 200
No = 1 | 0 | 0
| SCORE | 200
NOTES:
2/ Do you have a formal project Management Process in place |  |  | 50
Yes = 1 | 1 | 50
No = 4 | 0 | 0
| SCORE | 50
NOTES:
2/ How experienced in project management is the Project Manager |  |  | 35
None or very little experience = 4 | 0 | 0
Somewhat experienced = 3 | 3 | 105
Experienced = 2 | 0 | 0
Very Experienced = 1 | 0 | 0
| SCORE | 105
NOTES:
3/ Has the Project Manager managed a project of this size/scope |  |  | 35
No = 4 | 0 | 0
1 of similar in size = 3 | 0 | 0
1 to 2 larger in size = 2 | 2 | 70
Many equal to or larger = 1 | 0 | 0
| SCORE | 70
NOTES:
4/ Project Manager managed a project in this Organization to completion |  |  | 50
No = 4 | 4 | 200
1 or more = 1 | 0 | 0
| SCORE | 200
NOTES:
4/ Project Manager certified in Project Management processes |  |  | 20
No = 4 | 0 | 0
Yes = 1 | 1 | 20
| SCORE | 20
NOTES:
5/ Do the required skills to complete the project exist in-house, will outside contractors be required. |  |  | 50
No = 1 | 0 | 0
Somewhat = 2 | 2 | 100
Yes = 3 | 0 | 0
| SCORE | 100
NOTES:
6/ Who does Project Manager report to |  |  | 30
Functional Manager = 3 | 0 | 0
Business Owner = 2 | 2 | 60
Sponsor = 1 | 0 | 0
| SCORE | 60
NOTES:
7/ Was the last project managed by this project manager a success |  |  | 40
No = 3 | 0 | 0
Somewhat = 2 | 0 | 0
Yes = 1 | 1 | 40
| SCORE | 40
NOTES:
TOTAL RISK RATING
Low Risk 01 - 400
Medium Risk 101 - 650
High Risk 651 - xxx
| TOTAL SCORE | 845

## Technology
PROJECT TECHNOLOGY | Value | Score | Weight
1/ How many vendors / departments are involved in project |  |  | 30
1 = 0 | 0 | 0
2 = 1 | 2 | 60
3 = 2 | 0 | 0
More than 3 = 4 | 0 | 0
| SCORE | 60
NOTES:
2/ What is the number of estimated transactions per day |  |  | 40
Less than 5,000 = 1 | 1 | 40
5,000 to 50,000 = 2 | 0 | 0
50,000 to 100,000 = 3 | 0 | 0
Greater Than 100,000 = 4 | 0 | 0
| SCORE | 40
NOTES:
3/ Project / technology changes will effect |  |  | 30
Department = 0 | 0 | 0
Single Site = 1 | 0 | 0
Unit / Group / Region = 2 | 2 | 60
Enterprise = 4 | 0 | 0
| SCORE | 60
NOTES:
4/ Project / technology requirements are clear / complete / stable / documented |  |  | 30
Yes = 0 | 0 | 0
mostly = 1 | 0 | 0
somewhat = 2 | 2 | 60
Working on them = 3 | 0 | 0
Not Yet = 4 | 0 | 0
| SCORE | 60
NOTES:
5/ Technology to be used is fully matured |  |  | 30
Industry Standard fully matured = 0 | 0 | 0
Over 50% of technology is industry matured = 1 | 0 | 0
Less than 25% of technology is industry matured = 2 | 2 | 60
Technology is beta or non-industry accepted = 4 | 0 | 0
| SCORE | 60
NOTES:
6/ Does sufficient skills / infrastructure exist in this enterprise to execute the technology required. |  |  | 40
No = 4 | 0 | 0
Some = 3 | 3 | 120
Most all = 2 | 0 | 0
All requirements met = 1 | 0 | 0
| SCORE | 120
NOTES:
7/ New tools, procedures, training required |  |  | 30
No = 0 | 0 | 0
Somewhat = 2 | 0 | 0
Yes = 3 | 3 | 90
| SCORE | 90
NOTES:
8/ Has the technology been used before in this enterprise, was it successful |  |  | 40
No = 4 | 0 | 0
Some = 3 | 3 | 120
Most all = 2 | 0 | 0
All requirements met = 1 | 0 | 0
| SCORE | 120
NOTES:
9/ Will the technology be acquired (off the shelf) or developed |  |  | 30
Purchased off the shelf = 1 | 0 | 0
Acquired with some modification = 2 | 0 | 0
Acquired with significant modification = 3 | 0 | 0
Self Developed = 4 | 4 | 120
| SCORE | 120
NOTES:
10/ Does the implementation require vendor / contractor assistance |  |  | 40
None = 0 | 0 | 0
Some = 1 | 0 | 0
Significant = 3 | 3 | 120
Reliant on vendors = 4 | 0 | 0
| SCORE | 120
NOTES:
11/ Does a formal testing / user verification process exist |  |  | 30
Yes = 1 | 1 | 30
No = 4 | 0 | 0
| SCORE | 30
TOTAL RISK RATING
Low Risk 01 - 500
Medium Risk 501 - 780
High Risk 781 - xxx
| TOTAL SCORE | 880
|  |  |  | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0 | RISK VALUE | 0

## Planning
PROJECT PLANNING | Value | Score | Weight
1/ Does project involve new processes |  |  | 20
No = 0 | 0 | 0
Mix / old and new = 1 | 0 | 0
New = 2 | 2 | 40
| SCORE | 40
NOTES:
2/ Sufficient resources committed to complete project |  |  | 30
No = 4 | 0 | 0
Somewhat = 2 | 0 | 0
Yes = 1 | 1 | 30
| SCORE | 30
NOTES:
3/ Project deliverables are clearly defined |  |  | 50
No = 3 | 0 | 0
Somewhat = 2 | 2 | 100
Yes = 1 | 0 | 0
| SCORE | 100
NOTES:
4/ Scale and scope of project clearly defined |  |  | 50
No = 3 | 0 | 0
Somewhat = 2 | 2 | 100
Yes = 1 | 0 | 0
| SCORE | 100
NOTES:
5/ How complicated are the business requirements |  |  | 30
Very = 3 | 0 | 0
Somewhat = 2 | 0 | 0
Not very = 1 | 1 | 0
| SCORE | 0
NOTES:
6/ How complicated are the system requirements |  |  | 30
Very = 3 | 0 | 0
Somewhat = 2 | 0 | 0
Not very = 1 | 1 | 30
| SCORE | 30
NOTES:
7/ Will a defined project management structure / process be used to manage the project. |  |  | 50
Yes = 1 | 0 | 0
Somewhat = 2 | 2 | 100
No = 3 | 0 | 0
| SCORE | 100
NOTES:
8/ Do clearly defined project requirements and documentation exist |  |  | 30
Yes = 1 | 0 | 0
Somewhat = 2 | 2 | 60
No = 4 | 0 | 0
| SCORE | 60
NOTES:
9/ Is project dependant on other projects / systems being completed |  |  | 50
None - independent = 1 | 1 | 50
Some depenacies = 2 | 0 | 0
Highly dependant = 4 | 0 | 0
| SCORE | 50
NOTES:
10/ How many systems interfaces - major (not file) |  |  | 40
Zero to 2 = 1 | 0 | 0
3 to 5 = 2 | 2 | 80
6 or Greater = 3 | 0 | 0
| SCORE | 80
NOTES:
11/ How experienced is the project team in relation to the technical details of the project. |  |  | 40
Very = 1 | 0 | 0
Somewhat = 2 | 2 | 80
Not very = 3 | 0 | 0
| SCORE | 80
NOTES:
12/ Geographic location of project team members |  |  | 20
Primarily onsite = 1 | 1 | 20
Mix Onsite/Offsite = 2 | 0 | 0
Primarily offsite = 3 | 0 | 0
| SCORE | 20
NOTES:
13/ Project team members makeup |  |  | 20
All employees = 1 | 0 | 0
Mix EE's and vendors = 2 | 2 | 40
Primarily vendors = 3 | 0 | 0
| SCORE | 40
NOTES:
14/ Will project require organizational process or procedure changes to be made |  |  | 50
Yes, Major changes = 4 | 0 | 0
Somewhat, medium impact = 2 | 2 | 100
No, minor impact = 1 | 0 | 0
| SCORE | 100
NOTES:
15/ Team member commitment |  |  | 30
Dedicated full time = 1 | 0 | 0
Mixed w/other projects = 2 | 2 | 60
Squeeze time in = 4 | 0 | 0
| SCORE | 60
16/ Is the project time boxed (drop dead). Legal, contractual, regulatory |  |  | 50
No = 1 | 1 | 50
Some What (within given quarter) = 2 | 0 | 0
Yes = 4 | 0 | 0
| SCORE | 50
NOTES:
TOTAL RISK RATING
Low Risk 00 - 600
Medium Risk 601 - 900
High Risk 901 - xxx
| TOTAL SCORE | 840

## Contracts Resouorces
PROJECT Resources / Contracts | Value | Score | Weight
1/ Vendor supplied industry standard product |  |  | 40
No = 4 | 4 | 160
Somewhat = 1 | 0 | 0
Yes = 1 | 0 | 0
| SCORE | 160
NOTES:
2/ Are we a vendor beta site |  |  | 50
No = 1 | 0 | 0
Somewhat = 2 | 2 | 100
Yes = 4 | 0 | 0
| SCORE | 100
NOTES:
3/ Was a competitive assessment of the vendor done. |  |  | 30
No = 4 | 4 | 120
Somewhat = 2 | 0 | 0
Yes = 1 | 0 | 0
| SCORE | 120
NOTES:
4/ In how many locations has the vendor placed their systems / services |  |  | 40
None = 5 | 0 | 0
1 to 10 = 2 | 2 | 80
More than 10 = 1 | 0 | 0
| SCORE | 80
NOTES:
5/ Adequacy of vendor documentation |  |  | 20
Not = 4 | 0 | 0
Somewhat = 2 | 2 | 40
Adequate = 1 | 0 | 0
| SCORE | 40
NOTES:
6/ Prior usage of this vendor |  |  | 40
Not used before = 4 | 4 | 160
Used somewhat satisfied = 2 | 0 | 0
Multiple usage - satisfied = 1 | 0 | 0
| SCORE | 160
NOTES:
7/ Vendor company size (employees) |  |  | 40
1 to 5 employees = 4 | 4 | 160
6 to 50 employees = 2 | 0 | 0
Greater then 50 employees = 1 | 0 | 0
| SCORE | 160
NOTES:
8/ If the vendor must be replaced, how easy will it be |  |  | 40
Cannot replace = 5 | 0 | 0
Medium difficulty = 2 | 2 | 80
Easy = 1 | 0 | 0
| SCORE | 80
NOTES:
9/ Who is responsible for ongoing support? |  |  | 20
we are = 3 | 3 | 60
Vendor contracted = 2 | 0 | 0
| SCORE | 60
NOTES:
10/ Does the vendor supply training and materials |  |  | 20
No = 3 | 0 | 0
Yes = 1 | 1 | 20
| SCORE | 20
NOTES:
11/ Has the contract (type) been reviewed for risk ownership |  |  | 20
Don’t' Know = 4 | 4 | 80
We own the risk = 2 | 0 | 0
Contractor / Vendor owns risk = 1 | 0 | 0
| SCORE | 80
NOTES:
12/ Single source Contractor / Contract |  |  | 20
multiple contract companies / vendors = 4 | 0 | 0
1 contractor / vendor = 1 | 1 | 20
One Prime contractor / multiple sub contractors - vendors = 3 | 0 | 0
| SCORE | 20
NOTES:
13/ Does the contract contain enforceable vendor performance penalties / guarantees |  |  | 20
Don't Know = 3 | 3
No = 4 | 0 | 0
Yes = 1 | 0 | 0
| SCORE | 0
NOTES:
14/ Has background / security checks been performed on all perspective contactors / vendors being used. |  |  | 20
No = 4 | 0 | 0
Don't Know = 4 | 4
Yes = 1 | 0 | 0
| SCORE | 0
NOTES:
15/ Is the contractor / vendor development on or offshore development |  |  | 20
Don't Know = 4 | 0 | 0
Offshore development = 3 | 0
Domestic (onshore) development = 1 | 1 | 20
| SCORE | 20
NOTES:
16/ Does the contract contained a defined change control procedure |  |  | 20
Don't Know = 4 | 4 | 80
NO = 3 | 0
YES = 1 | 0 | 0
| SCORE | 80
NOTES:
17/ Who has direct control / authority of contractors / vendors / sub contractors |  |  | 20
Don't Know = 4 | 0 | 0
Prime contractor / vendor = 3 | 0 | 0
Internal management = 2 | 2 | 40
Project Manager = 1 | 0 | 0
| SCORE | 40
NOTES:
TOTAL RISK RATING
Low Risk 01 - 625
Medium Risk 626 -930
High Risk 931 - xxx
| TOTAL SCORE | 1000

## InternalResources
Internal Resources | Value | Score | Weight
1/ Do dependencies exist from external products or services that will affect the workload. |  |  | 20
No = 1 | 0 | 0
Mix / Some = 21 | 2 | 40
Yes = 4 | 0 | 0
| SCORE | 40
NOTES:
2/ Sufficient resources committed to complete project within the company |  |  | 30
No = 4 | 0 | 0
Somewhat = 2 | 2 | 60
Yes = 1 | 0 | 0
| SCORE | 60
NOTES:
3/ Is internal resource availability dependant on other project completions |  |  | 40
No = 1 | 0 | 0
Some = 2 | 2 | 80
Yes = 3 | 0 | 0
| SCORE | 80
NOTES:
4/ Technical requirements, deliverables and scope of project clearly defined |  |  | 50
No = 3 | 0 | 0
Yes = 1 | 1 | 50
| SCORE | 50
NOTES:
5/ Who has primary control of the project team members |  |  | 20
Project Manager = 1 | 0 | 0
Team Managers = 2 | 2 | 40
Functional Managers = 3 | 0 | 0
Contractor / Vendor = 4 | 0 | 0
| SCORE | 40
NOTES:
6/ All resource Managers fully support the implementation of this project |  |  | 40
No = 4 | 0 | 0
Some = 2 | 2 | 80
Yes = 1 | 0 | 0
| SCORE | 80
7/ Organizational workload is |  |  | 20
Light = 1 | 0 | 0
About right = 2 | 0 | 0
Stretched = 3 | 3 | 0
Consistent Overtime required = 4 | 0 | 0
| SCORE | 0
NOTES:
8/ All technical skills are available within the organization |  |  | 30
No = 4 | 0 | 0
Some = 2 | 2 | 60
Yes = 1 | 0 | 0
| SCORE | 60
NOTES:
9/ Morale of internal resources / organization is |  |  | 30
Poor = 4 | 0 | 0
Fair = 3 | 3 | 90
Good = 1 | 0 | 0
| SCORE | 90
NOTES:
10/ Project sponsor is easily available / responsive to issues |  |  | 30
No = 3 | 0 | 0
Some What = 2 | 2 | 60
Yes = 1 | 0 | 0
| SCORE | 60
NOTES:
11/ Project sponsor is enthusiastic and fully supports the project effort |  |  | 30
Some what = 3 | 0 | 0
Very = 1 | 1 | 30
| SCORE | 30
NOTES:
11/ Are - Will politics affect the project management and lifecycle? |  |  | 20
No = 3 | 0 | 0
Some What = 2 | 2 | 40
Yes = 1 | 0 | 0
| SCORE | 40
NOTES:
12/ Are - Will politics affect the technical decision made during project life cycle |  |  | 20
No = 1 | 0 | 0
Some What = 2 | 2 | 40
Yes = 3 | 0 | 0
| SCORE | 40
NOTES:
13/ Who developed the resource requirements / budget for the project |  |  | 20
Project Plan = 1 | 0 | 0
Project Manager estimate = 2 | 0 | 0
Organizational / Functional Managers = 3 | 3 | 0
Contractor / Vendor = 4 | 0 | 0
| SCORE | 0
NOTES:
14/ Who has primary control of the budget |  |  | 20
Project Manager = 1 | 0 | 0
Project Manager w/ limitations = 2 | 0 | 0
Business / functional manager = 3 | 3 | 0
Project Sponsor (total control) = 4 | 0 | 0
| SCORE | 0
NOTES:
15/ How acceptable is the organization to the changes being made (resistance) |  |  | 30
Set in stone processes / procedures = 4 | 0 | 0
Have to drag them along = 3 | 0 | 0
Go - kicking and screaming = 2 | 0 | 0
Willingly accept change = 1 | 1 | 30
| SCORE | 30
NOTES:
TOTAL RISK RATING
Low Risk 01 - 525
Medium Risk 526 -860
High Risk 861 - xxx
| TOTAL SCORE | 700

## Risk Summary
RISK ANALYSIS SUMMARY
| SCORES | HIGH RISK LEVEL
Project Initiate | 820 | >540
Project Manager | 845 | >650
Project Technology | 880 | >780
Project Planning | 840 | >900
Project Contracts / Resources | 1000 | >930
Project Internal Resources | 700 | >860
TOTAL PROJECT RISK VALUE |  | 5085
LOW RISK 0 to 3200
MEDIUM RISK 3201 to 4659
HIGH RISK 4600 to xxxx